## Tabelle1
Name | Description | Probability | Impact | Factor | Mitigation | Person in Charge
Backend-Frontend-Connection failed | Can't connect Backend to Frontend via HTTP-Request | 50% | 8 | 4 | Research regarding HTTP-Request | Patrick, Peter
Springboot not working | Springboot is new for us, error handling difficult | 20% | 8 | 1.6 | reserving additional time for code review / correction | Jennifer
WEB-App can't be implemented | only one Teammember is trained in using HTML/CSS/JS | 10% | 8 | 0.8 | additional Teammembers learn Web-App-Development | Patrick
Teammember lost | Teammember quits Team (various reasons) | 1% | 10 | 0.1